## Sheet1
Bug ID | Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot | Environment
BUG-001 | Login accepts invalid email format | Open Login → Enter “abc@@gmail” → Enter valid password → Submit | Validation message should appear for invalid email | Login form submits without email validation | Major | High | ss1.png | Chrome Latest
BUG-002 | Search shows unrelated products | Search for “Shoes” → Observe results | Only shoe-related items should appear | Unrelated categories appear in results | Medium | Medium | ss2.png | Chrome Latest
BUG-003 | Product image fails to load on PDP | Open any product → Check main image | Image should load correctly | Broken image icon displayed | Major | High | ss3.png | Firefox Latest
BUG-004 | Cart total not updating after quantity change | Add product → Go to cart → Change qty from 1 to 2 → Update | Total price should recalculate correctly | Total price remains unchanged | Critical | High | ss4.png | Chrome Latest
BUG-005 | Checkout allows empty address fields | Login → Add product → Checkout → Leave “Address” empty → Submit | Validation error should appear | Order continues without validation | Critical | High | ss5.png | Chrome Latest
BUG-006 | Order confirmation page shows blank order ID | Place order → Go to confirmation screen | Order ID should be visible | Order ID field is blank | Major | Medium | ss6.png | Firefox Latest
BUG-007 | Remove from cart button not working | Open cart → Click “X” to remove item | Item should be removed | Nothing happens; item remains | Major | High | ss7.png | Chrome Latest
BUG-008 | Search bar freezes when typing fast | Click search bar → Type fast (“DressDressDress”) | Search bar should accept input normally | Input gets stuck / slow response | Medium | Low | ss8.png | Chrome Latest
BUG-009 | Account logout still shows username | Login → Logout → Go to homepage | Username should disappear | User still sees “Logged in as …” | Major | High | ss9.png | Firefox Latest
BUG-010 | Mobile view breaks product grid | Open site in responsive mode (iPhone X) → Scroll | Product grid should be 2-column | Grid becomes overlapping | Major | Medium | ss10.png | Chrome DevTools